Version 1.0_December 2025

SRF Research and Training Centres

SRF Grants Management Office    (SRF-GMO)

Manual and SOPs

# SRF-RTC GRANTS MANAGEMENT GUIDELINES AND STANDARD OPERATING PROCEDURES (SOPs)

Table of Contents

Preamble	5

1. Introduction and Purpose	5

2. Scope of Application	5

3. Guiding Principles	6

4. Governance and Roles	6

5. Grant Lifecycle	7

STANDARD OPERATING PROCEDURES (SOPs)	8

Standard Operating Procedures (SOPs) For SRF–RTCs Grants Management Office (GMO) For External Grants (Primary Recipient & Sub-awardee Roles)	9

1. PRE-AWARD PHASE	9

2. AWARD PHASE	10

3. START-UP PHASE	11

4. IMPLEMENTATION PHASE	11

5. AUDIT & EVALUATION PHASE	13

6. GRANT CLOSE OUT PHASE	14

7. POST-CLOSEOUT PHASE	15

Standard Operating Procedures for Grants offered by or through SRF-RTCs  including sub-awardees	28

SOP 1: Grant Solicitation and Application Submission	28

Objective	28

Procedure	28

SOP 2: Peer Review and Funding Decision	28

Procedure	28

SOP 3: Award, Contracting, and Grant File Setup	29

Procedure	29

SOP 4: Financial Management and Disbursement	29

Procedure	29

SOP 5: Technical and Financial Reporting	29

Reporting Frequency	29

Required Elements	29

SOP 6: Monitoring, Audit, and Compliance	30

Monitoring Activities	30

Audit	30

SOP 7: Grant Closeout	30

Procedure	30

ANNEXES	30

ANNEX A: Standard Budget Template	30

ANNEX B: Allowable and Unallowable Cost Matrix	31

ANNEX C: Procurement Threshold & Method Matrix	31

ANNEX D: Subaward Compliance & Due Diligence Checklist	31

ANNEX E: Quarterly & Final Report Templates	32

ANNEX F: Asset Management & Disposal Register	32

ANNEX G: Risk Classification & Mitigation Matrix	32

List of figures

Figure 1. Grant Lifecycle	6

# Preamble

## 1. Introduction and Purpose

The Soar Research Foundation Research and Training Centres (SRF-RTCs) Grants Management Guidelines and Standard Operating Procedures (SOPs) provide a formal framework for the solicitation, awarding, management, monitoring, reporting, and closeout of research grants handled at SRF Research and Training Centres. SRF-RTCs hold primary responsibility for grant administration, financial stewardship, compliance, and reporting to external donors, while maintaining alignment with SRF institutional standards and guidelines.

These guidelines ensure:

- Efficient utilization of grant resources.

- Compliance with donor, institutional, national, and international regulations.

- Accountability, transparency, and equitable financial practices.

- Strengthening of research governance and capacity within RTCs.

## 2. Scope of Application

These guidelines apply to:

- All externally funded research grants administered at RTC level.

- Internal competitive research grants or fellowships awarded within SRF-RTCs.

- Sub-awards issued by RTCs to collaborating institutions.

- Consultancy, research service contracts, and collaborative research funding entering the RTC.

These guidelines shall be observed by:

- RTC Directors

- Principal Investigators (PIs)

- Grant Managers and Officers

- Finance and Procurement Units

- Research Ethics and Governance Committees

- Monitoring, Evaluation, and Learning (MEL) Units

## 3. Guiding Principles

- Accountability: All funds must be used solely for approved project purposes.

- Transparency: Decisions, processes, and expenditures must be traceable and justifiable.

- Financial Stewardship: Costs must be reasonable, allowable, and allocable.

- Compliance: Adherence to donor, institutional, and national financial regulations.

- Equity and Inclusion: Fair access to funding opportunities regardless of gender, institution, or seniority.

- Integrity: Zero tolerance for fraud, misappropriation, and ethical misconduct.

## 4. Governance and Roles

The following cadre of staff work together to constitute the SRF-RTC grants management team for each individual research or program grant.

| Role | Key Responsibilities |
| --- | --- |
| RTC Executive Director | Is the legal representative of the Organization. He or She authorizes grant submissions, approves major financial decisions, ensures RTC compliance. |
| Principal Investigator (PI) | Provides scientific leadership, supervises research activities, ensures timely reporting and compliance. |
| Grants Manager/Officer | Oversees grant administration, documentation, budgeting, reporting schedules, and donor communications. |
| Finance Unit | Executes financial transactions, prepares expense justifications, manages audits and procurement. |
| Procurement Unit | Manages tendering, quotations, vendor selection, contract issuance, and asset tracking. |
| Monitoring, Evaluation and Learning (MEL) Unit | Tracks deliverables, outputs, outcomes, learning, and evaluation indicators. |
| Ethics and Regulatory Unit | Ensures research ethics approvals, renewals, and compliance with human/animal subjects policies. |

## 5. Grant Lifecycle

- Pre-Award Phase: Call for proposals, eligibility screening, concept/proposal development, budget formulation, approval.

- Award and Contracting: Negotiation of terms, finalization of grant agreement, establishment of grant file and financial code.

- Implementation and Financial Management: Activity execution, procurement, expenditure monitoring, record-keeping.

- Monitoring, Evaluation and Reporting: Progress reviews, financial and technical reporting, midterm evaluation.

- Closeout: Final reporting, audit, asset disposition, documentation archiving.

Figure 1. Grant Lifecycle

# STANDARD OPERATING PROCEDURES (SOPs)

## Standard Operating Procedures (SOPs) For SRF–RTCs Grants Management Office (GMO) For External Grants (Primary Recipient & Sub-awardee Roles)

### 1. PRE-AWARD PHASE

#### 1.1 Opportunity Identification & Screening

Objective: Ensure SRF pursues only eligible, strategic, and feasible funding opportunities.
Procedures:

- GMO scans funding alerts (donors, networks, platforms) weekly.

- Program Leads flag potential calls to GMO using an Opportunity Intake Form (see appendix 1).

- GMO conducts eligibility check (mandate fit, geographic scope, financial thresholds, restrictions).

- GMO convenes a Bid/No-Bid Review Meeting with ED, Director of Research, Program Leads, and Finance.

- Decision recorded and shared within 24-48 hours.

#### 1.2 Proposal Planning & Design

Objective: Ensure structured development of competitive, compliant proposals.
Procedures:

- GMO appoints a Proposal Coordinator.

- Proposal Team established (technical, finance, M&E, procurement, community representative or engagement officer).

- Develop proposal timeline and assign tasks.

- Hold a proposal design workshop for technical alignment.

- GMO develops compliance checklist (donor rules, page limits, annexes).

- Finance drafts preliminary budget with Program Lead.

- M&E designs theory of change/logic model.

- Draft reviewed internally by senior management.

- GMO ensures all required attachments are prepared.

- ED approves final package before submission.

#### 1.3 Pre-Award Due Diligence

Objective: Provide donor with required organizational documentation.
Procedures:

- GMO compiles legally registered documents (registration, tax certificates, policies, audits).

- Finance provides financial statements, bank details, cost rates.

- HR provides staff organogram, CVs, key personnel information.

- Grants team completes donor due diligence questionnaires.

- GMO archives all submitted documentation.

### 2. AWARD PHASE

#### 2.1 Award Negotiation & Acceptance

Procedures:

- GMO reviews donor notification letter and award terms.

- Hold internal award review meeting (GMO, Finance, ED, Program Lead and Legal officer where needed).

- Identify compliance requirements, risks, reporting obligations.

- Negotiations with donor on budget, scope, or terms if required.

- ED signs award agreement.

- GMO circulates Award Summary Memo (Appendix 2) to key departments.

#### 2.2 Sub-award Management (When SRF is Prime)

Procedures:

- Identify sub-awardees via competitive or strategic selection.

- Conduct partner due diligence (financial capacity, systems, risk assessment).

- Draft sub-award agreement using approved templates.

- Legal and ED approve agreements.

- Hold a sub-award kick-off meeting to orient partners.

- Register each sub-award in SRF Grants Register (Appendix 3).

#### 2.3 Subaward Receipt Management (When SRF is Sub-awardee)

Procedures:

- Review the prime recipient’s sub-award agreement.

- Clarify expectations, deliverables, and reporting timelines.

- ED signs agreement after GMO and Finance clearance.

- GMO uploads agreement into the SRF grant repository (Appendix 4).

### 3. START-UP PHASE

#### 3.1 Internal Kick-Off Meeting

Procedures:

- GMO organizes kickoff within 10 days of award.

- Review goals, indicators, budget, timelines, partners, and risks.

- Assign internal roles: PI, Finance Lead, M&E Lead, Communications, Procurement.

- Agree on internal reporting lines and escalation procedures.

#### 3.2 Project Setup

Procedures:

- Finance sets up grant codes in accounting system.

- M&E develops indicator reference sheets and baseline plans.

- HR initiates staff recruitment if required.

- Procurement prepares procurement plan.

- GMO sets up grant folders (shared drive + physical file).

- Develop compliance matrix (donor rules, terms, deadlines).

### 4. IMPLEMENTATION PHASE

#### 4.1 Program Implementation Oversight

Procedures:

- Program Lead executes activities per approved workplan.

- GMO monitors compliance with workplan and donor rules.

- Monthly technical progress meetings held with GMO and M&E.

- Adjustments require GMO approval and donor notification (if needed).

#### 4.2 Financial Management

Procedures:

- Finance prepares monthly expenditure reports vs budget.

- GMO reviews budget burn rate and flags overspend/underspend.

- Monthly reconciliation with Program Lead.

- Ensure allowable, allocable, and correctly supported expenditures.

- Donor prior approvals obtained before restricted costs.

- Manage cash requests per donor schedules.

- Implement internal controls: segregation of duties, receipts, timesheets.

#### 4.3 Procurement & Asset Management

Procedures:

- Procurement follows approved procurement plan.

- Adhere to donor procurement thresholds.

- Maintain bid documents, vendor evaluations, contracts.

- Register assets in asset register.

- Label assets with donor and SRF codes.

- Conduct quarterly asset verification.

#### 4.4 Sub-Award Monitoring (When SRF is Prime)

Procedures:

- GMO conducts quarterly partner review meetings.

- Review program progress, financial reports, compliance, and deliverables.

- Conduct field verification visits at least 2x per year.

- Ensure partners submit timely narrative and financial reports.

- Provide technical support to strengthen partner capacity.

- Document and resolve any non-compliance issues.

#### 4.5 Reporting (Narrative & Financial)

Procedures:

- GMO maintains reporting calendar.

- Program Lead drafts narrative report using donor templates.

- M&E validates data and indicators.

- Finance prepares financial report.

- GMO conducts quality review against compliance checklist.

- ED approves before submission.

- GMO submits to donor on time and archives all reports.

#### 4.6 Risk Management & Compliance Oversight

Procedures:

- Maintain grant-specific risk register.

- Quarterly internal compliance review (GMO + Finance + Program).

- Implement corrective actions for identified risks.

- Ensure safeguarding, ethical research, data protection, anti-fraud measures.

- Document any incidents and report to donor as required.

### 5. AUDIT & EVALUATION PHASE

#### 5.1 Internal Audit

Procedures:

- Finance and GMO prepare grant files for internal audits.

- Auditors review financial transactions, procurement, documentation.

- GMO supports onsite verification visits.

- Management responds to audit queries and recommendations.

- Implement corrective actions.

#### 5.2 External/Donor Audits

Procedures:

- GMO receives audit notice and informs responsible staff.

- Compile required documents in an audit room (physical or electronic).

- Facilitate interviews and field visits.

- Respond to audit findings through management letters.

- Track closure of audit recommendations.

#### 5.3 Monitoring & Evaluation / Learning Reviews

Procedures:

- M&E team conducts baseline, midline, and endline assessments where applicable.

- Document lessons learned and best practices.

- Prepare briefs, dashboards, and learning products.

- Share findings with donor, partners, and SRF leadership.

### 6. GRANT CLOSE OUT PHASE

#### 6.1 Administrative Closeout

Procedures:

- GMO reviews award terms for closeout obligations.

- Notify departments and sub-awardees 90 days before end date.

- Ensure all deliverables are completed.

- Collect all partner closeout documents (if prime).

- Archive all files in grant repository (could be a cloud space).

#### 6.2 Financial Closeout

Procedures:

- Finance conducts final budget reconciliation.

- Identify unspent balances for donor return.

- Prepare final financial report with full supporting documents.

- GMO reviews and submits to donor.

#### 6.3 Asset Handover / Disposition

Procedures:

- Conduct final asset verification.

- Follow donor guidelines for asset disposition (transfer, sale, retention).

- Document asset handover using formal forms (Appendix 5).

- Update asset register.

#### 6.4 Final Narrative Report & Exit Meeting

Procedures:

- Program Lead prepares final report with M&E data.

- GMO ensures all compliance requirements are included.

- ED approves and GMO submits to donor.

- Conduct internal exit meeting to discuss performance and lessons.

- Record lessons in SRF Knowledge Management System (Appendix 6).

### 7. POST-CLOSEOUT PHASE

#### 7.1 Records Retention

Procedures:

- GMO archives grant documents for required retention period (usually 5–7 years).

- Maintain organized digital and physical files.

- Restrict file access to authorized persons only.

#### 7.2 Sustainability & Follow-On Opportunities

Procedures:

- Program Leads review opportunities for scale-up or extension.

- GMO identifies new funding aligned to lessons and gaps.

- Update SRF institutional track record using project achievements.

## Standard Operating Procedures for Grants offered by or through SRF-RTCs  including sub-awardees

## SOP 1: Grant Solicitation and Application Submission

### Objective

To ensure fair, transparent, and merit-based selection of research proposals.

### Procedure

- Issuance of Call

  - RTC issues call via website, email, internal bulletins.

- Eligibility Screening

  - Grants Office confirms institutional affiliation, compliance status, eligibility.

- Proposal Submission

  - Applicants submit proposal, CVs, budget, ethics status.

- Administrative Compliance Check

  - Verify completeness; non-compliant applications are returned without review.

## SOP 2: Peer Review and Funding Decision

### Procedure

- Reviewer Assignment

  - Minimum two independent reviewers.

- Scoring based on:

  - Scientific merit

  - Feasibility

  - Ethical considerations

  - Budget justification

- Grants Committee Decision

  - Final ranking, recommendations for approval/rejection.

- Notification

  - Written communication to all applicants.

## SOP 3: Award, Contracting, and Grant File Setup

### Procedure

- Draft and sign grant agreement.

- Create Grant File (physical & digital).

- Assign budget code and cost centers.

- Conduct PI orientation on compliance, procurement, reporting.

## SOP 4: Financial Management and Disbursement

### Procedure

- Disbursement follows approved budget and schedule.

- All expenses must be:

  - Allowable

  - Justified

  - Supported with receipts/invoices

- Procurement follows SRF-RTC Procurement Policy.

- Finance records all transactions in accounting system.

## SOP 5: Technical and Financial Reporting

### Reporting Frequency

| Report Type | Frequency |
| --- | --- |
| Technical Progress Report | Quarterly |
| Financial Report | Quarterly |
| Annual Consolidated Report | Annually |
| Final Completion Report | At Closeout |

### Required Elements

- Activities conducted

- Results achieved

- Challenges and mitigation

- Expenditure vs. budget variance

## SOP 6: Monitoring, Audit, and Compliance

### Monitoring Activities

- Quarterly review meetings

- Site supervision visits

- Internal financial reviews

### Audit

- Annual internal audit

- External audit per donor/contract terms

Non-compliance triggers corrective action plans.

## SOP 7: Grant Closeout

### Procedure

- Submit final narrative and financial reports.

- Final audit completed.

- Confirm asset inventory and disposition plan.

- Archive grant documentation for 7 years.

# ANNEXES

## ANNEX A: Standard Budget Template

Budget Template Structure:

| Cost Category | Item Description | Unit Cost | Quantity | Total Cost | Justification |
| --- | --- | --- | --- | --- | --- |
| Personnel | PI, Co-I, Research Assistants |  |  |  | Role & level of effort |
| Equipment | Laptops, lab equipment |  |  |  | Procurement plan required |
| Supplies & Materials | Field tools, lab reagents |  |  |  | Specify use and consumption rate |
| Travel & Fieldwork | Transport, accommodation, per diem |  |  |  | Indicate purpose and dates |
| Training & Workshops | Venue, materials, facilitation |  |  |  | Align with capacity building outcomes |
| Sub-awards/Collaborations | Partner institution support |  |  |  | Requires Subaward Checklist (Annex D) |
| Other Direct Costs | Communication, data management |  |  |  | Must be allowable |
| Indirect/Overhead Costs | Negotiated per grant (Option 3) |  |  |  | Document basis in contract |

## ANNEX B: Allowable and Unallowable Cost Matrix

| Category | Allowable | Unallowable |
| --- | --- | --- |
| Personnel | Salaries in approved budget | Salaries outside contract scope |
| Equipment | Pre-approved durable items | Luxury or personal-use devices |
| Travel | Project-related travel | Leisure or unapproved travel |
| Meals/Per Diem | Within approved rate | Alcoholic beverages, entertainment |
| Administrative Costs | Negotiated indirect costs | Double-charging overhead |

## ANNEX C: Procurement Threshold & Method Matrix

| Threshold (USD) | Method | Documentation Required |
| --- | --- | --- |
| < 500 | Direct Purchase | Receipt/Invoice |
| 500 - 5,000 | Three Quotations (RFQ) | Quotations & Evaluation Form |
| > 5,000 | Open Tender | Tender dossier, Evaluation Report, Award Minutes |

## ANNEX D: Subaward Compliance & Due Diligence Checklist

- Legal registration of partner institution

- Financial capacity and accounting system verified

- Procurement rules reviewed and aligned

- Signed subaward agreement

## ANNEX E: Quarterly & Final Report Templates

- Activities completed

- Outputs and progress against milestones

- Challenges and mitigation

- Updated budget vs expenditure table

## ANNEX F: Asset Management & Disposal Register

This includes: Asset Description, Serial Number, Acquisition Date, Custodian, Location, Condition, Disposal Recommendation.

## ANNEX G: Risk Classification & Mitigation Matrix

This includes Risk Type, Likelihood, Impact, Mitigation Measure, and Responsible Unit.

# APPENDICES

Appendix 1: Opportunity Intake Form

1. Basic Opportunity Information

- Opportunity Title:

- Donor / Funding Agency:

- Call / RFA / RFP Number:

- Link to Full Solicitation:

- Type of Funding:

☐ Grant

☐ Cooperative Agreement

☐ Contract

☐ Subaward (Prime: ______)

☐ Other (Specify)

- Opportunity Deadline(s):

  - Concept note deadline:

  - Full proposal deadline:

  - Questions due:

  - Registration deadlines (SAM, ERA Commons, EU Portal, etc.):

2. Eligibility & Strategic Fit Screening

- Eligibility Requirements (check all that SRF meets):

☐ Type of Organization eligible

☐ Geographic focus includes SRF/Uganda

☐ Past Performance requirements

☐ Financial capacity requirements

☐ Compliance (NICRA, Audits, Policies)

- Strategic Alignment (brief narrative):

  - Relevance to SRF Vision/Mission:

  - Fit with SRF Thematic Areas:

  - Fit with SRF–RTCs Research Priorities:

- Target Beneficiaries / Populations:

- Does SRF meet all mandatory conditions?

☐ Yes

☐ No

If No, specify risks.

3. Opportunity Summary

- Total Funding Available:

- Expected Award Size:

- Estimated Performance Period:

- Expected Start Date:

- Co-Funding / Cost Share Requirement:

☐ None

☐ Required (specify %)

- Number of Partners Needed:

- Major Deliverables / Requirements:

- Donor Priorities Highlighted in the Call:

4. Role of SRF

- SRF Intended Role:

☐ Prime Applicant

☐ Subawardee

☐ Consortium Lead

☐ Technical Partner

☐ Other, specify.........................................

- Proposed SRF Lead Department:
(Research, Innovation, Policy, M&E, RTCs, etc.)

- Key SRF Technical Contributions:

  - Brief description of planned scope.

5. Partner Information

- List of Potential Partners / Consortia:

- Contacts of Partner Institutions:

- Partner Strengths / Value Addition:

- Subaward Considerations:

- Past collaborations with SRF (if any):

6. Compliance & Risk Screening

Compliance Requirements

- USAID: ADS 303, NICRA, PSEA, Whistleblower

- NIH: Human subjects, clinical trials, biosafety, DUNS/SAM, ERA Commons

- EU: PRAG, visibility rules

- Global Fund: PU/DR, asset management

- Foundations: simplified reporting, flexibility

Risk Screening Checklist

- Financial Risk:

  - Award size too large/small?

  - Cost-share required?

- Technical Risk:

  - Limited technical capacity?

- Operational Risk:

  - Tight deadlines, complex procurement?

- Compliance Risk:

  - Complex donor requirements?

- Reputational Risk

Provide risk rating: ☐ Low ☐ Medium ☐ High

- Mitigation strategies:........................................................

7. Budget & Resource Needs

- Estimated SRF Budget Request:.................................

- Key Cost Categories:

  - Personnel

  - Travel

  - Equipment

  - Supplies

  - Subawards

  - M&E

  - Indirect Costs (using NICRA or donor ceiling)

- Additional Resources Required:

  - Consultants

  - Equipment

  - New staff

  - System upgrades

8. Internal Assessment & Decision

A. Technical Review

- Summary of technical feasibility

- Reviewer comments

B. Grants & Compliance Review

- Review of donor policies

- Eligibility confirmation

- Risk management notes

C. Finance Review

- Funding adequacy

- Budget feasibility

- Cost-share review

D. SMT/Leadership Decision

☐ Approved for Proposal Development

☐ Approved with Conditions

☐ Deferred

☐ Declined

Reasons for decision:
(Short explanation)

9. Proposal Development Plan (if approved)

- Proposal Lead / PI

- Proposal Manager

- Technical Writers Assigned

- Budget Team Assigned

- Partner Engagement Plan

- Submission Timeline with Key Milestones

- Go/No-Go Final Approval Date

10. Required Attachments

☐ Full Call Text

☐ Donor Guidelines

☐ Budget Template

☐ Eligibility Checklist

☐ Draft concept/notes

☐ Partner profiles/CVs

☐ Risk register (if high-risk)

Appendix 2: SRF – Award Summary Memo Template

To:
Executive Director / Senior Management Team / Grants Committee

From:
[Name], Grants Manager / Program Lead

Date:
Subject:
Award Summary – [Donor Name] / [Project Title]

1. Award Overview

- Donor/Funding Agency:

- Donor Type: (e.g., USAID, NIH, Foundation, Corporate, UN Agency)

- Award Title:

- Program Area: (SRH, One Health, NCDs, Adolescent Health, etc.)

- Geographic Focus: (District(s), National, Regional)

- Implementation Period: (Start–End Date)

- Total Award Value: (USD)

- Cost Share Required: Yes/No (Amount/Percentage)

- Subawardees/Consortium Partners: (If applicable)

2. Strategic Alignment

- Relevance to SRF Strategy:
(How the award aligns with SRF’s mission, Vision 2040/AU Agenda 2063 contributions, gender empowerment, innovation, etc.)

- Value Addition:
(New partnerships, new research areas, capacity building, policy influence, etc.)

3. Scope of Work / Key Objectives

Provide 3–5 bullet points summarizing major objectives:

- Objective 1

- Objective 2

- Objective 3

- Objective 4

4. Deliverables & Milestones

- Key research activities or program interventions

- Expected milestones by quarter/year

- Required outputs (reports, datasets, publications, capacity building sessions, etc.)

5. Budget Summary

- Total Direct Costs:

- Indirect Costs (NICRA/applicable rate):

- Budget Notes:
(Major cost drivers, staffing, equipment, subawards, overhead limitations)

6. Compliance Requirements

Include donor-specific requirements:

- USAID: Branding & Marking, ADS 303, MERL Plan, Environmental Compliance, PSEA, FFATA

- NIH: Human subjects, data sharing, RPPR, biosafety

- EU/PRAG: Procurement thresholds, VAT rules, documentation requirements

- Global Fund: PU/DR, fixed assets, programmatic milestones

- Others: Reporting frequency, audit obligations, digital recordkeeping

7. Risks & Mitigation Measures

Identify key risks:

- Operational

- Compliance

- Financial

- Reputational

- Partner management
Then list mitigation strategies for each.

8. Key Personnel & Management Structure

- Principal Investigator / Project Lead

- Co-Investigators

- Technical Staff

- Finance & Compliance Officer

- M&E Lead

- Subaward/Partner Oversight

Attach an organogram if required.

9. Monitoring, Evaluation & Learning (MEL)

- Core indicators

- Reporting timelines

- Learning agenda

- Data protection & quality assurance approach

10. Subaward Management (If Applicable)

- Partner names

- Subaward values

- Roles & responsibilities

- Oversight plan (risk assessment, site visits, reporting)

11. Approvals Required

- Financial approval

- Compliance review clearance

- Leadership sign-off

- Board/Steering Committee approval (if required)

Signature blocks can be placed here.

12. Attachments

- Donor Notice of Award / Grant Agreement

- Budget & Budget Narrative

- Workplan / Logframe

- Risk Matrix

- Organizational & consortium structure

- Branding guidelines (if applicable)

Appendix 3. SRF Grants Register

| Grant ID | Donor | Project Title | Program Area | Geographic Scope | Award Amount (USD) | SRF Share | Cost Share Required | Funds Received | Expenditure to Date | Burn Rate (%) | Remaining Balance | Start Date | End Date | Status | Reporting Frequency | Last Report Submitted | Next Report Due | Audit Requirement | PI / Project Lead | Subaward Partners | Risk Level | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Appendix 4. SRF Grant repository

It’s designed to store, track, and manage all grant-related information in a structured, searchable way. This will be implemented in Excel, SharePoint, or a database.

1. Core Structure / Sections

A. Grant Master Information

| Field | Description | Example |
| --- | --- | --- |
| Grant ID | Unique internal identifier | GR001 |
| Donor | Funding organization | USAID, NIH |
| Project Title | Official project/grant name | Adolescent SRH Empowerment |
| Program Area | Area of focus | SRH, One Health, NCDs |
| Geographic Scope | Country, region, districts | Kampala, Wakiso |
| Start Date | Grant start date | 01-Jan-2025 |
| End Date | Grant end date | 31-Dec-2026 |
| Status | Current implementation status | On Track, Delayed, Closed |
| Grant Type | Research, Program, Capacity Building | Research |
| SRF Share | Amount allocated to SRF | 500,000 USD |
| Cost Share Required | Yes/No, details if applicable | No |

B. Financial Information

| Field | Description | Example |
| --- | --- | --- |
| Award Amount | Total approved funding | 750,000 USD |
| Funds Received | Cumulative funds received | 400,000 USD |
| Expenditure to Date | Amount spent | 350,000 USD |
| Burn Rate (%) | Formula: Expenditure ÷ Funds Received ×100 | 87.5% |
| Remaining Balance | Award Amount – Expenditure | 400,000 USD |
| Currency | USD, EUR, Local Currency | USD |

C. Reporting & Compliance

| Field | Description | Example |
| --- | --- | --- |
| Reporting Frequency | Quarterly, Biannual, Annual | Quarterly |
| Last Report Submitted | Date of last report | 30-Sep-2025 |
| Next Report Due | Upcoming reporting deadline | 31-Dec-2025 |
| Audit Requirement | Yes/No | Yes |
| Compliance Status | On Time / Overdue | On Time |
| Notes | Special remarks about reporting | Pending donor review |

D. Risk & Issues

| Field | Description | Example |
| --- | --- | --- |
| Risk Level | Low / Medium / High | Medium |
| Risk Category | Financial, Programmatic, Compliance, Operational | Financial |
| Issue Description | Brief description of the risk or challenge | Delayed disbursement |
| Mitigation Action | Steps to reduce risk | Follow up with donor |
| Owner / Responsible | SRF staff accountable | Dr. Allan B. |

E. Partners / Subawards

| Field | Description | Example |
| --- | --- | --- |
| Partner Name | External organization | Partner A |
| Funding Amount | Amount allocated to partner | 100,000 USD |
| Reporting Status | On Time / Overdue | On Time |
| Risk Level | Low / Medium / High | Low |
| Notes | Special considerations | Conditional funding |

F. Documentation / Repository Links

| Field | Description | Example |
| --- | --- | --- |
| Grant Agreement | Link / path to signed agreement | /Grants/GR001/Agreement.pdf |
| Workplan | Link / path to project workplan | /Grants/GR001/Workplan.xlsx |
| Budget | Approved budget document | /Grants/GR001/Budget.xlsx |
| Reports | Link to submitted reports | /Grants/GR001/Reports/ |
| Audit Reports | Link to audit documents | /Grants/GR001/Audit.pdf |
| Other Documents | MOUs, correspondence, deliverables | /Grants/GR001/Correspondence.pdf |

G. Notes & Observations

| Field | Description | Example |
| --- | --- | --- |
| Lessons Learned | Key insights from implementation | Community engagement critical |
| Next Steps / Follow-up | Actions for ongoing compliance | Prepare final report |
| Internal Comments | For SRF staff tracking | Monitor burn rate closely |

2. Additional Features / Best Practices

- Unique Grant ID: Ensure every grant has a unique identifier.

- Dynamic Linking: Links to all grant documents stored in a structured folder.

- Searchable Fields: Donor, Program Area, Status, Risk Level.

- Conditional Formatting: Highlight overdue reports, high-risk grants, or near-expiry grants.

- Dashboard Integration: The repository should feed a dashboard showing KPIs like total grants, burn rate, reporting compliance, and risk overview.

- Version Control: Track updates in documents or financials over time.

Appendix 5. SRF ASSET HANDOVER FORM

This template is designed to standardize the transfer of SRF assets between departments, projects, or staff while ensuring accountability and proper documentation.

Form No.: ___________
Date of Handover: ___ / ___ / _______

1. Handover Details

| Field | Description |
| --- | --- |
| Handover From (Department/Staff) | ________________________ |
| Handover To (Department/Staff) | ________________________ |
| Project / Grant / Program | ________________________ |
| Reason for Handover | ________________________ |

2. Asset Details

| S/N | Asset Name / Description | Asset ID / Serial No. | Quantity | Unit Condition (New/Good/Fair/Poor) | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |

Attach additional sheets if necessary.

3. Verification

Received By (Handover To):
Name: ___________________________
Designation: _____________________
Signature: _______________________
Date: ___ / ___ / _______

Delivered By (Handover From):
Name: ___________________________
Designation: _____________________
Signature: _______________________
Date: ___ / ___ / _______

4. Asset Condition Confirmation

| Field | Description |
| --- | --- |
| Overall Condition of Assets | Good / Fair / Poor (circle) |
| Missing / Damaged Items Noted | Yes / No (circle) |
| Notes / Comments | ________________________ |

5. Approvals

| Approver | Designation | Signature | Date |
| --- | --- | --- | --- |
| Department Head | ____________ | ____________ | ___ / ___ / _______ |
| Finance / Asset Custodian | ____________ | ____________ | ___ / ___ / _______ |
| Project / Program Manager | ____________ | ____________ | ___ / ___ / _______ |

Instructions / Notes:

- All assets must be listed with their serial numbers or unique identifiers.

- Physical verification must be done before signing.

- Any damages or missing items must be documented in the Remarks column.

- Copies of the completed form must be retained by both Handover From and Handover To departments.

- Asset condition should be assessed honestly to avoid discrepancies.

Appendix 6. SRF Knowledge Management System

This template for the SRF Knowledge Management System (KMS) is to be used after the completion of a grant. The goal is to systematically capture lessons learned, best practices, outputs, and resources to inform future projects, promote organizational learning, and facilitate reporting and knowledge sharing.

Grant ID: __________________
Project Title: __________________
Donor: __________________
Program Area: __________________
Project Duration: From ___ / ___ / _______ to ___ / ___ / _______
Project Lead / PI: __________________

1. Executive Summary

| Field | Description |
| --- | --- |
| Project Objectives | Summarize the main goals of the grant/project |
| Key Achievements / Outcomes | Highlight significant outputs and results |
| Challenges / Constraints | Major hurdles faced during implementation |
| Recommendations for Future Projects | Lessons learned and suggested improvements |

2. Knowledge Assets / Outputs

| S/N | Asset Type | Title / Description | Link / Location | Accessibility | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Report | Final Project Report | /Grants/GR001/Report.pdf | Internal / Public | – |
| 2 | Policy Brief | SRH Policy Brief | /Grants/GR001/PolicyBrief.pdf | Internal / Public | – |
| 3 | Data Set | Survey Results | /Grants/GR001/Data.xlsx | Internal | Requires permission |
| 4 | Training Material | Workshop PPT | /Grants/GR001/Training/Slides.pptx | Internal | – |
| 5 | Publication | Journal Article | DOI / Link | Public | – |

Attach additional sheets if necessary.

3. Lessons Learned

| Theme / Area | Observation / Lesson | Impact | Recommendation / Action |
| --- | --- | --- | --- |
| Community Engagement | Engaging local leaders increased uptake | Improved participation | Start engagement earlier in future projects |
| Data Collection | Paper-based surveys caused delays | Reduced timeliness | Use digital data collection methods |
| Collaboration | Partner coordination challenges | Affected reporting timelines | Hold monthly coordination meetings |

4. Success Stories / Case Studies

| S/N | Story / Case Study Title | Summary | Link / Reference | Responsible Staff |
| --- | --- | --- | --- | --- |
| 1 | Adolescent SRH Champions | Girls became peer educators | /Grants/GR001/CaseStudy1.pdf | Dr. Jane A. |
| 2 | One Health Surveillance | Early detection of zoonotic disease | /Grants/GR002/CaseStudy2.pdf | Dr. Allan B. |

5. Recommendations for Knowledge Sharing

| Activity | Target Audience | Channel / Platform | Responsible Staff | Timeline |
| --- | --- | --- | --- | --- |
| Webinar | SRF Staff & Partners | Zoom / Teams | Project Lead | Month 1 post-completion |
| Policy Brief Dissemination | Ministry / Donor | Email / Website | PI | Month 2 post-completion |
| Internal Workshop | SRF Staff | In-person / Hybrid | KM Officer | Month 1 post-completion |
| Knowledge Repository Upload | SRF KMS | SharePoint / Cloud | KM Officer | Immediately after close-out |

6. Grant Impact Assessment

| Indicator | Target | Actual Achieved | Notes |
| --- | --- | --- | --- |
| Number of beneficiaries reached | 500 | 620 | Target exceeded |
| Policy changes influenced | 1 | 1 | Incorporated in National Guidelines |
| Staff trained | 20 | 25 | Peer educators included |

7. Supporting Documents / References

| Document Type | File Name / Link | Notes |
| --- | --- | --- |
| Final Report | /Grants/GR001/FinalReport.pdf | – |
| Budget / Financial Report | /Grants/GR001/Budget.xlsx | – |
| Data Sets | /Grants/GR001/Data.xlsx | Restricted access |
| Publications | DOI / Link | – |
| Photos / Media | /Grants/GR001/Media/ | Optional for dissemination |

8. KM Officer / Project Lead Sign-off

| Name | Designation | Signature | Date |
| --- | --- | --- | --- |
| ____________________ | __________________ | __________________ | ___ / ___ / _______ |
| ____________________ | __________________ | __________________ | ___ / ___ / _______ |

Notes / Guidelines:

- The template ensures all knowledge generated during a grant is captured systematically.

- Use links or references to files stored in the SRF cloud repository or SharePoint.

- Lessons learned should be specific, actionable, and tied to project implementation.

- Success stories can be shared internally or externally, depending on donor or privacy requirements.

- The completed KMS template should be uploaded to the SRF central Knowledge Management Repository.

Appendix 7. Fillable Budget Template (Dual Currency Format)

| Cost Category | Item Description | Unit Cost (Local Currency) | Unit Cost (USD) | Quantity | Total (Local) | Total (USD) | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Personnel |  |  |  |  |  |  |  |
| Equipment |  |  |  |  |  |  |  |
| Supplies & Materials |  |  |  |  |  |  |  |
| Travel & Fieldwork |  |  |  |  |  |  |  |
| Workshops/Training |  |  |  |  |  |  |  |
| Sub-Awards/Partners |  |  |  |  |  |  |  |
| Other Direct Costs |  |  |  |  |  |  |  |
| Indirect / Overhead Costs | Negotiated (%) |  |  |  |  |  | Describe negotiated basis |

Appendix 8. Quarterly Financial Reporting Template

| Budget Line | Approved Budget (Local) | Approved Budget (USD) | Expenditure This Quarter (Local) | Expenditure This Quarter (USD) | Cumulative Expenditure (Local) | Cumulative Expenditure (USD) | Variance (Local) | Variance (USD) | Explanation of Variance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Certification:

- Prepared by (Finance Officer): __________________ Date: __________

- Reviewed by (Grants Manager): __________________ Date: __________

- Approved by (RTC Director): __________________ Date: __________

Appendix 9. Subaward Due Diligence & Compliance Form

Partner Institution Name: __________________________

| Verification Item | Yes/No | Evidence/Notes |
| --- | --- | --- |
| - Legal Registration Confirmed |  |  |
| - Financial Management System Exists |  |  |
| - Procurement Policy Reviewed & Compatible |  |  |
| - Previous Grant Performance Satisfactory |  |  |
| - Key Personnel CVs Verified |  |  |
| - Safeguarding / Ethics Policies in Place |  |  |

Approval Recommendation: ☐ Approve ☐ Approve with Conditions ☐ Reject

Signatures:

- Grants Officer: _____________________ Date: ________

- RTC Director: _______________________ Date: ________

Appendix 10. Workplan & Milestone Tracking Template

| Activity | Deliverable/Output | Responsible Person | Start Date | End Date | Status (Not Started / In Progress / Completed) | Notes |
| --- | --- | --- | --- | --- | --- | --- |

Appendix 11.  SRF Internal Audit Checklist for Grants

This is designed to ensure compliance with donor requirements, organizational policies, and good financial and programmatic practices. It will be implemented as an Excel sheet, Word checklist, or internal audit form.

Grant ID:__________________
Project Title:__________________
Donor:__________________
Audit Period: From ___ / ___ / _______ to ___ / ___ / _______
Auditor Name: __________________

1. Governance and Documentation

| # | Audit Item | Check | Status (Yes/No) | Notes / Comments |
| --- | --- | --- | --- | --- |
| 1 | Approved grant agreement on file | Copy available |  |  |
| 2 | Signed MoUs / Subaward agreements attached |  |  |  |
| 3 | Workplan and budget approved |  |  |  |
| 4 | Project objectives clearly documented |  |  |  |
| 5 | Organizational policies followed (finance, procurement, HR) |  |  |  |

2. Financial Management

| # | Audit Item | Check | Status (Yes/No) | Notes / Comments |
| --- | --- | --- | --- | --- |
| 6 | Funds received match donor disbursement schedule |  |  |  |
| 7 | Expenditure is supported by invoices, receipts, or payment vouchers |  |  |  |
| 8 | Budget allocations adhered to |  |  |  |
| 9 | Burn rate and remaining balance reconciled |  |  |  |
| 10 | Cost share requirements documented and fulfilled |  |  |  |
| 11 | Bank reconciliations completed and up to date |  |  |  |
| 12 | Asset register updated with project assets |  |  |  |

3. Procurement

| # | Audit Item | Check | Status (Yes/No) | Notes / Comments |
| --- | --- | --- | --- | --- |
| 13 | Procurement followed donor/organizational guidelines |  |  |  |
| 14 | Competitive bidding or quotes obtained |  |  |  |
| 15 | Contracts and purchase orders documented |  |  |  |
| 16 | Goods/services delivered and verified |  |  |  |
| 17 | Vendor payments authorized and recorded |  |  |  |

4. Programmatic Compliance

| # | Audit Item | Check | Status (Yes/No) | Notes / Comments |
| --- | --- | --- | --- | --- |
| 18 | Activities conducted as per approved workplan |  |  |  |
| 19 | Beneficiaries reached documented |  |  |  |
| 20 | Reports submitted on time and complete |  |  |  |
| 21 | Data collection and monitoring conducted according to protocol |  |  |  |
| 22 | Subaward partners monitored |  |  |  |

5. Risk Management

| # | Audit Item | Check | Status (Yes/No) | Notes / Comments |
| --- | --- | --- | --- | --- |
| 23 | Risks identified and documented |  |  |  |
| 24 | Mitigation actions implemented |  |  |  |
| 25 | High-risk items escalated to management |  |  |  |
| 26 | Insurance or coverage requirements met (if applicable) |  |  |  |

6. Asset Management

| # | Audit Item | Check | Status (Yes/No) | Notes / Comments |
| --- | --- | --- | --- | --- |
| 27 | Project assets recorded in SRF asset register |  |  |  |
| 28 | Assets physically verified |  |  |  |
| 29 | Handover / disposal documents complete (if applicable) |  |  |  |

7. Reporting & Knowledge Management

| # | Audit Item | Check | Status (Yes/No) | Notes / Comments |
| --- | --- | --- | --- | --- |
| 30 | Final reports submitted to donor |  |  |  |
| 31 | Lessons learned captured in KMS |  |  |  |
| 32 | Success stories / case studies documented |  |  |  |
| 33 | Documentation uploaded to central repository |  |  |  |

8. Overall Audit Conclusion

| Field | Notes |
| --- | --- |
| Major Observations |  |
| Key Recommendations |  |
| Overall Compliance Rating | High / Medium / Low |
| Auditor Signature | ___________________ |
| Date | ___ / ___ / _______ |
| Project Lead / Manager Acknowledgment | ___________________ |
| Date | ___ / ___ / _______ |

Instructions / Notes:

- Use the checklist during periodic internal audits or at project close-out.

- Status “Yes” indicates compliance; “No” indicates action needed.

- Notes should capture details of non-compliance, corrective actions, or observations.

- This checklist can be integrated into an Excel workbook with tabs for each section, formulas for summary compliance % and conditional formatting for quick visual review.